## Sheet1 (hidden)
Name | Meaning
Adhrit | Lord Vishnu
Lakshay | Target
Nirav | Silent
Prayag | Confluence of the Ganga, Jamuna and Saraswati rivers
Samarth | Efficient
Sashwat | Permanent, perpetual
Nivaan | True worrior, Champion
shreyansh | Fame,wealth
shreyash | Fame

## Sheet2
Defect | Description | Status of the defect | Assigned To | Comments | Comment by Developers | QA Comments | Date of testing
#84 | In “Contact Us” page Central time drop down arrow is displaying wrong | Fixed |  | Fixed |  | Verified, working as expected | 2017-02-20
#83 | Drop down arrow mark in black color | Fixed |  | Fixed |  | Verified, working as expected | 2017-02-20
#82 | Premium also seen as black color | Invalid bug |  | It is as expected |  | Expected behavior of the application | 2017-02-20
#81 | Typekit font not loaded for affordability flow | New |  | It is as per the prototype design. |  | Affordability first page heading is in smaller case(Chris has provided in smaller case in the prototype) | 2017-02-20
#80 | Scroll bar in financial rating page not required | Fixed |  | Fixed | UI Issue | Verified, working as expected | 2017-02-20
#79 | Default gender is male in “I am not sure how much I need” flow | Fixed |  |  |  | Verified, working as expected | 2017-02-09
#78 | Smoker/Non-Smoker field looks different in Chrome and IE. | Fixed |  | Browser issue | Browser issue | Browser issue | 2017-02-20
#77 | Smoker rate table mismatch | Fixed |  |  |  | Verified, working as expected | 2017-02-07
#76 | I know how much I need leads to contact us page | Not reproducible |  |  |  | Not able to reproduce | 2017-02-07
#75 | Premium value displayed 0 | Fixed |  |  |  | Verified, working as expected | 2017-02-07
#74 | Enter values for affordability flow,click Start My Quote button,Click Ourlifecovered logo from the next screen and navigate to affordability landing page,coverage value displayed wrong. | Fixed | Venkat |  |  | Verified, working as expected | 2017-02-07
#73 | User is able to select 25$ from the dropdown. This field should be non-editable and should default to value selected in the previous screen | Fixed |  |  |  | Verified, working as expected | 2017-02-07
#72 | The values in monthly premium and number of coverage years fields are not greyed out like the other dropdown values | Fixed |  |  |  | Verified, working as expected | 2017-02-07
#71 | Default gender set to male forI am not sure how much I need flow | Fixed |  |  |  | Verified, working as expected | 2017-02-07
#70 | Default gender set to male for I know how much I need flow | Fixed |  |  |  | Verified, working as expected | 2017-02-07
#69 | If user selected smoker, the rate does not stay as Standard Smoker for I am not sure how much I need flow | Fixed |  |  |  | Verified, working as expected | 2017-02-07
#68 | If user selected smoker, the rate does not stay as Standard Smoker for I know how much I need flow | Fixed |  |  |  | Verified, working as expected | 2017-02-07
#67 | SINGLE CARRIER PAGE FOOTER WRONG | Fixed | Venkat |  |  | Verified, working as expected | 2017-02-07
#66 | Email address is editable in natural language page | Fixed |  |  |  | Verified, working as expected | 2017-02-07
#65 | Smoker and non-smoker same coverage amount | Fixed |  |  |  | Verified, working as expected | 2017-02-07
#64 | drop down look and feel is different for smoker/non-smoker section | Fixed |  |  |  | Verified, working as expected | 2017-02-07
#63 | Text not displaying correctly in IE | Fixed |  |  |  |  | 2017-02-03
#62 | Transamerica premiums are having much difference than other carriers | New |  |  |  | Defect not fixed due to DOB validation | 2017-02-03
#61 | Clicking on Home icon or right click and open home link leads to error page | Fixed | Venkat |  |  |  | 2017-02-03
#60 | Coverage amount is blank | Fixed |  |  |  | EBIX issue. We are not able to reproduce after we poined to EBIX production end point URL | 2017-02-20
#59 | drop down look and feel is different in IE and Chrome | Fixed |  |  |  | verified working as expected | 2017-01-25
#58 | Coverage and premium displayed wrong in single carrier | New |  |  |  | Defect not fixed due to DOB validation | 2017-01-25
#57 | Coverage automatically change in second journey from $50,000 to $100,000 | New |  |  |  | Defect not fixed due to DOB validation | 2017-01-25
#56 | Premium value is wrong | New |  |  |  | Defect not fixed due to DOB validation | 2017-01-25
#55 | I need to be able to see how the name, etc is being displayed in Rgility. The last time I was able to go to Rgility, the first and last name were populating the First name field. We do not use a last name in MyLifeCovered.net, only the newer sites such as the Our Life Covered sites. We need to make sure all of the fields are transferring to Rgility correctly. We will also need to make sure that the first and last name are transferred into Hubspot correctly | Fixed | Jyoti |  |  | Can not verify | 2017-01-20
#54 | The rates shown after the full calculator go up when I slide down to lower coverage amounts | Need more info | Venkat |  |  | Dev team needs information on this | 2017-01-20
#53 | After clicking “Apply Now” the link to Rgility is not working | Duplicate |  |  |  | Same as #50 | 2017-01-20
#52 | When I got to the quote, the rates for the other life insurance companies were not right. Then I moved the slider to change the benefit amount and the amounts then changed to what look to be correct amounts. | Unable to reproduce | Venkat |  |  | Unable to reproduce | 2017-01-20
#51 | On the natural quote form, the drop down for the I Know What I Want journey had the new benefit amounts | Fixed | Krishna |  |  | Need clarification from Dev | 2017-01-20
#50 | The “Thank you for applying. We will get back to you soon.” Message is back. | Fixed |  |  |  | Verified. Working as expected | 2017-01-20
#49 | In all three quote instances, the slider will not go below $100,000 in coverage. | Fixed | Venkat |  |  | Verified. Working as expected | 2017-01-20
#48 | The Full Calculator doesn’t allow for coverage amounts under $100,000 | Fixed | Krishna |  |  | Need clarification from Dev | 2017-01-20
#47 | The drop down for the coverage amounts (on both the natural quote form and standard quote form) should include the new coverage amounts of $25K, $50K, $75K, $100K, $150k $250K, $500K and $1MM. | Fixed | Venkat |  |  | Verified. Working as expected | 2017-01-20
#46 | On the natural quote form, the periods at the end of the “I want the number of coverage years to be” | Fixed | Jyoti |  |  | Verified. Working as expected | 2017-01-23
#45 | No validation of age and year of birth | New |  |  |  | Defect not fixed due to DOB validation | 2017-01-25
#44 | Alignment issues in natural language pages | Fixed | Jyoti |  |  | Verified. Working as expected | 2017-01-20
#43 | Cookies issue in natural language page | Fixed | Jyoti |  |  | Verified. Working as expected
#42 | First and last name validations | Fixed | Jyoti |  |  | Verified. Working as expected
#41 | Newly created typekit font enabled | Fixed | Venkat |  |  | Verified. Working as expected | 2017-01-31
#40 | Accepting logically wrong phone number | Not a bug |  |  |  | Invalid defect, hence no fix | 2017-01-23
#39 | Right click home link leads to blank page | Fixed |  |  |  | Verified. Working as expected | 2017-01-23
#38 | “Calculate Need” application moved to next page but stayed only for 1 second. Without any user input it, moved unexpectedly from natural language page to contact us page | Fixed | Jyoti |  |  | Verified. Working as expected | 2017-01-20
#37 | Unexpectedly moving to contact us page | Fixed |  |  |  | Verified. Working as expected | 2017-01-20
#36 | Application not navigating to metcon page | Fixed |  |  |  | Verified. Working as expected | 2017-01-20
#35 | System accepts logically wrong email ids | Fixed |  |  |  | Verified. Working as expected | 2017-01-20
#34 | 3rd social networking site symbol missing in footer section | Duplicate | Krishna |  |  | Invalid defect, hence no fix
#33 | JavaScript error preventing playing of video bug | Fixed | Jyoti |  |  | Verified. Working as expected in VM | 2017-01-31
#32 | Multicarrier - stray code in the header bug | Duplicate | Venkat | Chris has provided the fix. | The changes is not in our hand, which is Rgility site. | Verified. Working as expected
#31 | X symbol in text box in IE bug | Fixed | Venkat | Chris has provided the fix | Code incorporated-fixed. | Verified. Working as expected
#30 | Dropdown arrow in IE browser bug | Fixed | Venkat | Chris has provided the fix | Code incorporated-fixed. | Verified. Working as expected
#29 | URL error bug | Not able to reproduce | Jyoti |  |  | Able to replicate in new build | 2017-01-31
#28 | Unexpected code displayed bug | Duplicate | Krishna | Chris has provided the fix |  | Duplicated of #32
#27 | Coverage amount displayed as 0 bug | Fixed | Krishna | Chris has provided the fix |  | Invalid defect, hence no fix
#26 | Need different logo for multicarrier bug | Fixed | Krishna | Chris has provided the fix |  | Verified. Working as expected. Displays the phone number as passed in the url
#25 | Multicarrier-I know what I want path last name blank bug | Fixed | Venkat |  | Issue got fixed(cookies still not update for last name) | Verified. Working as expected
#24 | Multicarrier-I know what I want path default coverage amount bug | Fixed | Venkat |  | Issue fixed. | Verified. Working as expected
#23 | Only show amount per month on Affordability path bug | Fixed | Jyoti |  | Issue fixed. | Verified. Working as expected
#22 | Incorrect tracking code displayed in the Privacy forms for multicarrier. bug | Fixed | Krishna |  |  | Verified. Working as expected
#21 | Data displayed on "natural language" quote defaults incorrectly bug | Fixed | Jyoti |  | Issue fixed. | Verified. Working as expected
#20 | Mandatory fields are not displayed with asterisk on quote form bug | Not a bug | Venkat |  | Issue fixed. | Invalid defect, hence no fix | 2017-01-23
#19 | Captcha verification always shown negative bug | Deferred | Venkat |  | Unable to reproduce in local server. | Defect is deferred | 2017-01-31
#18 | Spacing and font size in footer bug | Fixed | Krishna | Chris has provided the fix |  | Verified. Working as expected
#17 | Social media icon missing from footer invalid | Invalid | Krishna | Chris has provided the fix |  | Invalid defect, hence no fix